## Product Development
Type | Status | Title | Start date | End date | Duration (in days) | % Complete | Assignee name | Assignee email | Note
Milestone |  | Train and validation sets online | 2020-11-18 | 2020-11-18 | - | -
Task |  | Training phase | 2020-11-18 | 2021-04-05 | 139 | 0
Milestone |  | Registration deadline for competition participants | 2021-03-31 | 2021-03-31 | - | -
Milestone |  | Test datasets available (task 1) | 2021-04-05 | 2021-04-05 | - | -
Milestone |  | Submission deadline for results (task 1) | 2021-04-09 | 2021-04-09 | - | -
Task |  | Test phase (task 1) | 2021-04-05 | 2021-04-09 | 5 | 0
Milestone |  | Test datasets available (tasks 2 and 3) | 2021-04-12 | 2021-04-12 | - | -
Milestone |  | Submission deadline for results (tasks 2 and 3) | 2021-04-16 | 2021-04-16 | - | -
Task |  | Test phase (tasks 2 and 3) | 2021-04-12 | 2021-04-16 | 5 | 0
Task |  | Write short method description | 2021-04-12 | 2021-04-23 | 12 | 0
Milestone |  | Method descriptions due | 2021-04-23 | 2021-04-23 | - | -
Milestone |  | Full data disclosure | 2021-07-01 | 2021-07-01 | - | - |  |  | Ground truth for test set, participant results.

## Sheet2
Start date | End date | Title | Tasks
| 2020-11-18 | Train and validation sets available | all
2020-11-18 | 2021-04-05 | Training phase | all
| 2021-03-31 | Registration deadline for competition participants | all
| 2021-04-05 | Test datasets available | 1
2021-04-05 | 2021-04-09 | Test phase | 1
| 2021-04-09 | Submission deadline for results | 1
| 2021-04-12 | Test datasets available | 2&3
2021-04-12 | 2021-04-16 | Test phase | 2&3
| 2021-04-16 | Submission deadline for results | 2&3
2021-04-12 | 2021-04-23 | Write short method description | all
| 2021-04-23 | Method descriptions due | all
| 2021-07-01 | Full data disclosure: round truth for test set, participant results. | all